## Daily Status
| In Progress |  | Completed today |  | Completed |  | Pending |  | Can't be automated because of Test data or Locators unavailability in App
Resource | Android - Mobile | iOS- iPhone | Android - Mobile | iOS-iPhone | Android - Mobile | iOS-iPhone | Android - Mobile | iOS-iPhone
Pramod | 1 | 0 | 2 | 0 | 108 | 13 | 72 | 297 | 13
Hari | 1 | 0 | 4 | 0 | 130 | 0
Total | 2 | 0 | 6 | 0 | 238 | 13
Total count of feasiblity yes |  |  |  |  | 310

## Current Pivot
S. No
Count of Automated
|  | Biz | Retail | (blank) | # Total |  |  |  | # Automatable | Completed %
S.No | Module
1 | Accounts | 25 | 30 |  | 55 |  |  |  | 58 | 94.8276
2 | Alerts | 3 | 1 |  | 4 |  |  |  | 6 | 66.6667
3 | Bill Pay | 17 | 17 |  | 34 |  |  |  | 36 | 94.4444
4 | Enrollment | 1 | 5 |  | 6 |  |  |  | 6 | 100
5 | Preferences | 19 | 18 |  | 37 |  |  |  | 39 | 94.8718
6 | Statements | 6 | 6 |  | 12 |  |  |  | 13 | 92.3077
7 | Transactions | 11 | 13 |  | 24 |  |  |  | 54 | 44.4444
8 | Transfers | 39 | 41 |  | 80 |  |  |  | 91 | 87.9121
(blank)
| # Total | 121 | 131 |  | 252 |  |  |  | 310 | 81.2903
2020-07-17
S. No | Completed Automation Status | Column Labels
|  | Business | # Business | Retail | # Retail | (blank) | # (blank) | # Total |  |  | Count of Automation Feasibility - Leslie | Column Labels
| Module | Yes |  | Yes |  | (blank) | [5 empty] | Biz | Retail | (blank) | # Automatable Scripts
1 | Accounts | 25 | 25 | 30 | 30 |  |  | 55 |  | S. No | Module
2 | Alerts | 3 | 3 | 1 | 1 |  |  | 4 |  | 1 | Accounts | 27 | 31 |  | 58
3 | Bill Pay | 12 | 12 | 16 | 16 |  |  | 28 |  | 2 | Alerts | 5 | 1 |  | 6
4 | Enrollment | 1 | 1 | 5 | 5 |  |  | 6 |  | 3 | Bill Pay | 18 | 18 |  | 36
5 | Preferences | 19 | 19 | 18 | 18 |  |  | 37 |  | 4 | Deposit Check | 3 | 4 |  | 7
6 | Statements | 6 | 6 | 6 | 6 |  |  | 12 |  | 5 | Enrollment | 1 | 5 |  | 6
7 | Transactions | 7 | 7 | 7 | 7 |  |  | 14 |  | 6 | Preferences | 21 | 18 |  | 39
8 | Transfers | 34 | 34 | 40 | 40 |  |  | 74 |  | 7 | Statements | 6 | 7 |  | 13
9 | (blank) | [8 empty] | 8 | Transactions | 23 | 31 |  | 54
| # Total | 107 | 107 | 123 | 123 |  |  | 230 |  | 9 | Transfers | 45 | 46 |  | 91
(blank)
[11 empty] | # Automatable Scripts | 149 | 161 |  | 310
2020-07-21
S. No | Completed Automation Status | Column Labels | [7 empty] | * Original Number of automated Scripts reduced from 323 because of the following
|  | Business | # Business | Retail | # Retail | (blank) | # (blank) | # Total |  | * 8 Enrollment Test Scripts are removed as per request from HW Team.
| Module | Yes |  | Yes |  | (blank) |  |  |  | * Locators are not available in app for few scripts and those cannot be automated
1 | Accounts | 25 | 25 | 30 | 30 |  |  | 55
2 | Alerts | 3 | 3 | 1 | 1 |  |  | 4 |  |  | 310
3 | Bill Pay | 14 | 14 | 16 | 16 |  |  | 30
4 | Enrollment | 1 | 1 | 5 | 5 |  |  | 6
5 | Preferences | 19 | 19 | 18 | 18 |  |  | 37 |  |  | # Automation Feasibility Yes | Column Labels
6 | Statements | 6 | 6 | 6 | 6 |  |  | 12 |  |  |  | Business | # Business | Retail | # Retail | (blank) | # (blank) | # Automatable Scripts
7 | Transactions | 11 | 11 | 12 | 12 |  |  | 23 |  | S. No | Module | Yes |  | Yes |  | (blank)
8 | Transfers | 37 | 37 | 41 | 41 |  |  | 78 |  | 1 | Accounts | 27 | 27 | 31 | 31 |  |  | 58
9 | (blank) | [8 empty] | 2 | Alerts | 5 | 5 | 1 | 1 |  |  | 6
| # Total | 116 | 116 | 129 | 129 |  |  | 245 |  | 3 | Bill Pay | 18 | 18 | 18 | 18 |  |  | 36
[10 empty] | 4 | Deposit Check | 3 | 3 | 4 | 4 |  |  | 7
[10 empty] | 5 | Enrollment | 1 | 1 | 5 | 5 |  |  | 6
[10 empty] | 6 | Preferences | 21 | 21 | 18 | 18 |  |  | 39
[10 empty] | 7 | Statements | 6 | 6 | 7 | 7 |  |  | 13
[10 empty] | 8 | Transactions | 23 | 23 | 31 | 31 |  |  | 54
[10 empty] | 9 | Transfers | 45 | 45 | 46 | 46 |  |  | 91
(blank)
[11 empty] | # Automatable Scripts | 149 | 149 | 161 | 161 |  |  | 310
[11 empty] | # Automation Feasibility Yes | Column Labels
[12 empty] | Business | # Business | Retail | # Retail | (blank) | # (blank) | # Automatable Scripts
[10 empty] | S. No | Module | Yes |  | Yes |  | (blank)
[10 empty] | 1 | Accounts | 27 | 27 | 31 | 31 |  |  | 58
[10 empty] | 2 | Alerts | 5 | 5 | 1 | 1 |  |  | 6
[10 empty] | 3 | Bill Pay | 18 | 18 | 18 | 18 |  |  | 36
[10 empty] | 4 | Deposit Check | 3 | 3 | 4 | 4 |  |  | 7
[10 empty] | 5 | Enrollment | 1 | 1 | 5 | 5 |  |  | 6
[10 empty] | 6 | Preferences | 21 | 21 | 18 | 18 |  |  | 39
[10 empty] | 7 | Statements | 6 | 6 | 7 | 7 |  |  | 13
[10 empty] | 8 | Transactions | 23 | 23 | 31 | 31 |  |  | 54
[10 empty] | 9 | Transfers | 45 | 45 | 46 | 46 |  |  | 91
(blank)
[11 empty] | # Automatable Scripts | 149 | 149 | 161 | 161 |  |  | 310

## Summary
Count of Automation Feasibility - Leslie | Automated | Automation Feasibility - Leslie
| No | No Total | Yes | Yes Total | Grand Total
Module | Yes |  | Yes
Accounts | 3 | 3 | 55 | 55 | 58
Alerts | 2 | 2 | 5 | 5 | 7
Bill Pay |  |  | 36 | 36 | 36
Deposit Check |  |  | 7 | 7 | 7
Enrollment |  |  | 6 | 6 | 6
Preferences | 2 | 2 | 36 | 36 | 38
Statements |  |  | 13 | 13 | 13
Transactions | 17 | 17 | 37 | 37 | 54
Transfers | 2 | 2 | 89 | 89 | 91
Grand Total | 26 | 26 | 284 | 284 | 310

## Login
Test Case Id | PhoneNumber | otp1 | otp2 | otp3 | otp4 | FullName | EmailID
Verifying the Login Functionality with Invalid OTP | 9347417320 | 1 | 2 | 3 | 4 | Mahesh | maheshpunna955@gmail.com

## CreateConsulatntFlow
Test Case Name | headerValue | headerValue1 | symptomsdescription | entertext | symptomsdescriptionskin
Verify if user is able to create a consultation | Enter Patient Details | Select your health problem | I am suffering from high fever and skin rashes since 2 days. I took dolo-650, but it didn't help. Please suggest medicines or tests that are required. | 2days | xyz

## Create Account In Terms and con
Testcase | Name | Phone number | E-mail | Password
Verifying Create Account Funtionality In Terms and Conditions Page | Mahesh | 8106314530 | mahesh.punnam@gmail.com | Mahesh@123

## Corporate Account
Testcase | Email | Password
Verifying Corporate Account | Test001@cognizant.com | 1980-01-01